## General SG
Action in rural Sussex Project Guidance/Monitoring for West Wittering Neighbourhood Plan
Version 7 (February 2018)
Ref | Task in Detail | Task Group/ Lead | % Complete | Action | Date by
TASKS COMPLETE
C1 | SWOT Analysis | BH | 90% | Will be finalised to go into draft plan
C2 | Village Lifestyle Analysis | KM, BH, RL | 80% | To be finalised to feed into contextual evidence
C3 | Stakeholder Letters | JB | 90% | Recored all letters sent,- no further action
C4 | Focus Group Leaders Identified | NP.AT.RS.WB | 100% | Completed
C5 | Undertake Call for Sites | SG/JB | 95%
C6 | Invite additional Questionnaires | SG/Airs | 95%
C7 | Identify Heritage, Assets & Treasures | NP/JB | 80% | Workshop done. JB and NP to write up report | mid Jan 18
C8 | Undertake a Housing Needs Assessment | JB/FB | 10% | Feedback to be sent to AECOM to commence study | mid Jan 18
TASKS IN PROGRESS
P1 | Focus Groups Reports | NP.AT.RS.WB |  | To produce draft reports by 15th Dec - to feed into draft plan | mid dec 17
P2 | Scoping Report (consultation) | AirS/SG | 60% | To be worked into draft SA/SEA for SG comments
P3 | Contextual Evicence Report | SG/AirS | 50% | Pending. Ongoing working document, to be updated | mid feb 18
P4 | Review Design Statement & Character Assessment (VDS) | NP/FG/ JB | 50% | To go to parish council for approval. It will be developed concurrent with NDP and cnsulted on at same time.
P5 | Tourism Survey (local businesses) | LE Group/ RS | 80% | Agree and action group. who? When? What questions? | mid Jan 18
P6 | Assess sites and write report | AirS / H FG | 35% | Housing profiles being compiled by Housing Group, to compile same profiles for all WW sites in CDC SHELAA | end feb 18
P7 | Flooding and drainage issues |  |  | PC carrying out a Flood Risk Mapping Project -
P8
P9
TASKS TO START
S2 | Biodiversity Conservation Designations Study | Angela Ward |  | contact Sussex Biodiversity record centre with list/map of all sites to produce bespoke report around these sites.
S3 | Prepare Draft Policies | AirS |  | Based on outcome of FG Findings/outcome
S4
S5